## Sheet1
Feature | Initial Estimate | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7 | Hours Left
Added further functionality to flask app | 20 | 2 | 4 | 4 | 4 | 0 | 4 | 2 | 0
Settting | Start | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7
Planned Hours |  | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5
Actual Hours |  | 2 | 4 | 4 | 4 | 0 | 4 | 2
Remaining Effort | 20 | 18 | 14 | 10 | 6 | 6 | 2 | 0
Ideal Burndown | 20 | 17.5 | 15 | 12.5 | 10 | 7.5 | 5 | 2.5